## Sheet1
Week | IDEAL APP
1 | Learn the Basics of App Development
2 | Implement the IDEAL Java Program into the App
3 | Test and Configure App
4 | Add Special Effects/Animations
5 | Add Music
6 | Present Finished Product and try to get it to the Android Market/Google Play